## Sheet1
ID | Task Name | Duration | Start | Finish | Predecessors
1 | Compiling ROS2 onto raspberry PI | 3 days | 2023-01-17 | 2023-01-19
2 | Modeling PI car with space models |  | 2023-01-20 |  | 4
3 | Formal Proposal |  | 2023-01-23
4 | System Identification |  | 2023-01-24 |  | 5,6,7
5 | Motor Testing
6 | IMU initial testing/setup/data grab | 7 days | 2023-01-27 | 2023-02-02
7 | Encoder initial testing/setup | 1 day | 2023-02-03 | 2023-02-03
8 | Lidar setup/initial test on sample code | 1 day | 2023-02-02 | 2023-02-02
9 | Servo initial testing | 1 day | 2023-02-03 | 2023-02-03