## Sheet1
ID | Task Name | Duration | Start | Finish | Predecessors
1 | Compiling ROS2 onto raspberry PI | 3 days | 2023-01-17 | 2023-01-19
2 | Modeling PI car with space models |  | 2023-01-20 |  | 3
3 | Formal Proposal |  | 2023-01-23
4 | System Identification |  | 2023-01-24
5 | Motor Testing
6 | IMU initial testing/setup | 3 days | 2023-01-27 | 2023-01-30
7 | Encoder initial testing/setup
8 | Lidar intial testing/setup